## Sheet1
Tasks To Be done | Week 12 | Week 13 1/3 | Week 13 2/3 | Week 13 3/3 | Week 13/14 | Week 14 1/3 | Week 14 2/3 | Week 14 3/3 | Week 15 1/3 | Week 15 2/3 | Week 15 3/3 | Week 16 1/2 | Week 16 2/2 | Week 17 1/2 | Week 17 2/2 | Week 18 | Week 19-21
Project planning and Initial Design | 6 Hours
Skeleton |  | 1-2 Hours
Data Exporting |  |  | 3-5 Hours
Data Management and Organization In CSV |  |  |  | 1-3 Hours
Data Object Implementation and Testing |  |  |  |  | 1-2 Hours
Pie-Chart Object Planning | [5 empty] | 1-2 Hours
Pie-Chart Object Implementation | [6 empty] | 1-3 Hours
Pie-Chart Object Drawing and Testing | [7 empty] | 3-5 Hours
Column Bar Object Planning | [8 empty] | 1-2 Hours
Column Bar Object Implementation | [9 empty] | 1-3 Hours
Column Bar Object Drawing and Testing | [10 empty] | 3-5 Hours
Implementing Year Selection Option | [11 empty] | 1-2 Hours
Testing and Debugging Year Selection Option | [12 empty] | 1-? Hours
Implementing Comparison Option | [13 empty] | 1-5 Hours
Testing and Debugging Comparison Option | [14 empty] | 1-? Hours
General Testing and Debugging | [15 empty] | 2-? Hours
Extras, Final Polish, and Submission | [16 empty] | 3-? Hours